## 3-Week Look-Ahead
3-WEEK LOOK-AHEAD SCHEDULE
Project |  |  |  | Start (Mon) | 2026-10-05 | Updated
[9 empty] | Week 1 | Week 2 | Week 3
# | Activity | Trade | Area / Location | Start | Finish | Crew | Constraints (RFI, submittal, inspection, delivery, predecessor) | Status
1 | Layout and form footings, Bldg A | Concrete | Grid A-D | 2026-10-05 | 2026-10-07 | 4 | Footing rebar submittal approved | On Track
2 | Footing inspection | Inspector | Grid A-D | 2026-10-08 | 2026-10-08 |  | Book city inspector 48 hrs ahead | At Risk
3 | Pour footings | Concrete | Grid A-D | 2026-10-09 | 2026-10-09 | 6 | Mix design approved; pump truck booked | On Track
4 | Underground plumbing rough-in | Plumbing | Bldg A slab | 2026-10-12 | 2026-10-16 | 3 | RFI-014 cleanout locations open | At Risk
5 | Under-slab inspection | Inspector | Bldg A slab | 2026-10-19 | 2026-10-19 |  |  | On Track
6 | Vapor barrier and slab prep | Concrete | Bldg A slab | 2026-10-20 | 2026-10-22 | 4 | Vapor barrier delivery 10/16 | On Track
Change the start date each Monday to roll the plan forward. Bars shade automatically from the Start and Finish columns. Scheduling software: https://aecify.com/features/project-scheduling