## Change Order Log
CO # | Date | Description | Reason | Cost Impact | Schedule Impact (days) | Status | Requested By | Approved By | Date Approved | Linked RFI | Notes
001 | 2026-03-10 | Add blocking for owner AV at Conference 210 | Owner request | 4200 | 2 | Approved | Owner's rep | Owner | 2026-03-18 | RFI-012
002 | 2026-03-22 | Unsuitable soils at Grid D footings | Unforeseen condition | 18500 | 5 | Submitted | GC |  |  | RFI-018 | Awaiting geotech letter

## Summary
AECify — Free Construction Change Order Log Template
Use one copy per project. Update Status as approvals land.
Approved cost impact
Submitted (not yet approved)
When backup, photos, and approvals outgrow the row, try AECify change orders: https://aecify.com/features/change-order-management