## Daily Report
Date | Weather | Temp High | Temp Low | Crew Count | Work Performed | Equipment | Deliveries | Visitors | Delays / Issues | Safety Notes | Reported By
2026-09-15 | Clear | 78 | 54 | 12 | Framed Level 2 corridor; hung HVAC mains in west wing | Scissor lift, boom lift | Hollow metal frames — Door Supply | Owner's rep 10:00–11:30 | None | Stretch-and-flex completed 6:45am | J. Ramirez, Superintendent
2026-09-16 | Light rain AM | 64 | 51 | 9 | Interior MEP rough-in; exterior work paused until 11:00 | Scissor lift | None | City inspector — plumbing rough | Rain delay ~3 hours on exterior | Wet floors — caution tape at entries | J. Ramirez, Superintendent

## Summary
AECify — Free Daily Construction Report Template
Use one workbook per project. Add one row at the end of each day.
Days logged
When photos and checklists belong with the day, try AECify inspections: https://aecify.com/features/inspection-reports