## Punch List
Item # | Location | Description | Trade | Priority | Status | Assigned To | Date Identified | Due Date | Date Closed | Notes
001 | Corridor 120 — north wall | Paint touch-up at door frame | Finish | Low | Open | ABC Painting | 2026-09-01 | 2026-09-15 |  | Photo on superintendent phone
002 | Electrical Room | Panel directory labels missing | Electrical | High | In Progress | Sparks Electric | 2026-09-02 | 2026-09-10
003 | Restroom 1F | Caulk joint at lavatory | Plumbing | Medium | Closed | Flow Plumbing | 2026-08-28 | 2026-09-05 | 2026-09-04 | Verified 2026-09-04

## Summary
AECify — Free Construction Punch List Template
Use one copy per project. Update Status as contractors respond.
Open / in progress
Closed
When photos and contractor replies outgrow the sheet, try AECify punch list: https://aecify.com/features/punch-list