## Schedule of Values
Item No. | Description of Work | Scheduled Value | From Previous Application | This Period | Materials Presently Stored | Total Completed and Stored to Date | % Complete | Balance to Finish | Retainage
01 | General conditions | 60000 | 18000 | 6000 | 0
02 | Sitework | 85000 | 85000 | 0 | 0
03 | Concrete | 140000 | 98000 | 28000 | 0
04 | Masonry | 45000 | 0 | 9000 | 4500
05 | Metals | 60000 | 0 | 0 | 12000
06 | Wood and carpentry | 70000 | 0 | 0 | 0
07 | Thermal and moisture protection | 55000 | 0 | 0 | 0
08 | Doors and windows | 65000 | 0 | 0 | 0
09 | Finishes | 90000 | 0 | 0 | 0
22-23 | Plumbing and HVAC | 110000 | 11000 | 16500 | 0
26 | Electrical | 70000 | 7000 | 10500 | 0
TOTALS

## Summary
AECify - Free Schedule of Values Template
Enter line items on the Schedule of Values tab. Before each new billing period, copy Total Completed and Stored into From Previous Application and clear This Period.
Retainage % (input) | 10%
Total scheduled value (SOV lines)
Approved change orders not yet on the SOV (input) | 0
Contract sum to date
Total completed and stored to date
Retainage
Total earned less retainage
Less previous certificates for payment (input) | 0
Current payment due
Balance to finish, including retainage
Not an official AIA document. When billing outgrows the spreadsheet, try AECify pay applications: https://aecify.com/features/pay-applications