## Submittal Log
Submittal # | Spec Section | Description | Discipline | Submitted By | Date Submitted | Reviewer | Date Required | Status | Revision | Date Returned | Ball in Court | Notes / Comments
001 | 03 30 00 | Cast-in-place concrete mix design | Structural | ABC Concrete | 2026-03-01 | Structural Engineer | 2026-03-15 | Approved | 0 | 2026-03-12 | — | Approved as noted — use Type II cement
002 | 08 11 13 | Hollow metal door frames — Level 1 | Architectural | Door Supply Co. | 2026-03-05 | Architect | 2026-03-20 | Revise & Resubmit | 0 | 2026-03-18 | Door Supply Co. | Provide fire rating labels on schedule
003 | 26 05 19 | Low-voltage cabling cutsheets | Electrical | Sparks Electric | 2026-03-08 | Electrical Engineer | 2026-03-22 | Under Review | 0 |  | Electrical Engineer

## Summary
AECify — Free Construction Submittal Log Template
Use one copy of this workbook per project. Update Status and Ball in Court as reviews progress.
Status counts (formulas reference Submittal Log column I):
Open / in progress
Approved (incl. as noted)
Rejected / closed
When you outgrow the spreadsheet, try AECify submittal tracking: https://aecify.com/features/submittal-tracking